## EMS ICCP Obj Requests
Set | Priority | StationName | DVVC | Status | PointsInDMSDDS | DateEMSICCPObjReqSent | DateEMSObjReceived | DateBatchedIntoDMSQAS | DateBatchedIntoDMSDDS | Notes | SwCtr
1 | 0 | AMADOR | Yes | Abandoned | NA | 2015-10-27
1 | 1 | CAMDEN |  | Done | Yes |  | 2015-10-08 | 2015-10-13 | 2016-01-04 |  | Orange County
1 | 1 | CHESTNUT | Yes | Done | Yes |  | 2015-10-08 | 2015-10-13 | 2016-01-04 |  | Orange County
1 | 1 | JOHANNA |  | Done | Yes | 2015-10-13 | 2015-10-13 | 2015-10-14 | 2016-01-04 | 5/6/2016 - status/analog points for Spades 12kV added to dmsdds; iccp requested for Spades 12kV o/o JOHANNA sub; 8/5/2016 - On both dmsqas & dmsdds, [1] added new iccp objects per Hui/Ben request, [2] removed replaced 1 iccp object (i.e. DMS_FAIRVW_12KV_BUS_PARALLEL_CB) because Nancy created another one, and [3] updated Spades iccp to be in data set 0001 instead of 0002 | Orange County
1 | 1 | MACARTHUR |  | Done | Yes |  |  |  | 2016-05-05 | ICCP objects added to dmsdds; points that already had other iccp objects referencing them were stripped out of batch file, so batch files for MACARTHUR on dmsqas are NOT the same as those on dmsdds, though they have the same filename | Orange County
1 | 2 | CABRILLO | Yes | Done | Yes | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-12-11 | Analog point 2407 was missing ICCP object--request sent to Nancy to create iccp for this missing point; iccp for AP 2407 added to dmsqas + dmsdds; 5/5/2016 Analog point 5477 was missing ICCP objects--request sent to Nancy for this; iccp for AP 5477 added to dmsqas + dmsdds | Orange County
1 | 2 | CROWN |  | Done | Yes | 2015-10-30 | 2015-11-09 | 2015-11-09 | 2016-05-06 | 5/6/2016 - iccp files on dmsqas batched into dmsdds, but Rutgers & Peninsula don't appear to be updated on CROWN display | Orange County
1 | 2 | EDGEWATER |  | Removed | Yes | 2015-10-30 | 2015-11-09 | 2015-11-09 | 2016-05-06 | 5/6/2016 - Ben added points to dmsdds; iccp objects added to dmsdds, although display for EDGEWATER not on either dms production or dmsqas yet; 7/29/2016 Removed iccp obj from dmsqas + dmsdds
1 | 2 | FAIRVIEW |  | Done | Yes | 2015-10-30 | 2015-11-03 | 2015-11-04 | 2016-01-04 | Nancy removed status point 107670, STINGER SWITCH from list per Gerardo | Orange County
1 | 2 | JERSEY | Yes | Done | InProgress | 2015-11-17 | 2015-11-25 | 2015-11-25 |  | Not OC
1 | 2 | SAN MIGUEL | Yes | Done | InProgress | 2015-11-17 | 2015-11-25 | 2015-11-25 |  | Not OC
2 | 3 | BARRE |  | In Progress | No | 2015-11-25 | 2015-12-04 |  |  | ICCP Objects only EMS Prod, not EMSQAS; status point 111935 "1164 BARRE SAS" not included because for 66kV | Orange County
2 | 3 | ELLIS | Yes | In Progress | No | 2015-12-15 | 2015-12-15 |  |  |  | Orange County
2 | 3 | IRVINE |  | In Progress | No | 2015-12-16 | 2016-01-11 |  |  |  | Orange County
2 | 3 | LA PALMA |  | In Progress | No | 2016-01-08 | 2016-01-11 |  |  |  | Orange County
2 | 3 | MORRO |  | In Progress | No | 2016-01-13 | 2016-01-14 |  |  |  | Orange County
2 | 3 | MOULTON |  | In Progress | No | 2016-01-13 | 2016-01-14 |  |  |  | Orange County
2 | 3 | ONEIL |  | In Progress | No | 2016-01-15 | 2016-01-20 |  |  |  | Orange County
2 | 3 | SHAWNEE |  | In Progress | No | 2016-01-15 | 2016-01-20 |  |  |  | Orange County
2 | 3 | TALBERT |  | In Progress | No | 2016-01-20 | 2016-01-28 |  |  |  | Orange County
2 | 3 | UNIVERSITY |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | APOLLO |  | Abandoned | NA |  |  |  |  | APOLLO shows up on ems as 66kv; Customer Sub | Orange County
2 | 4 | ATWOOD | Yes | In Progress | No | 2016-01-21 | 2016-02-02 |  |  |  | Orange County
2 | 4 | BOLSA | Yes | In Progress | No | 2016-01-21 | 2016-02-02 |  |  |  | Orange County
2 | 4 | BORREGO |  | In Progress | No | 2016-02-03 | 2016-02-16 |  |  |  | Orange County
2 | 4 | BREA | Yes | In Progress | No | 2016-02-03 | 2016-02-16 |  |  |  | Orange County
2 | 4 | BRYAN | Yes | In Progress | No | 2016-02-16 | 2016-03-01 |  |  |  | Orange County
2 | 4 | BURPIT |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | CANYON |  | In Progress | No | 2016-02-16 | 2016-03-01 |  |  |  | Orange County
2 | 4 | CAROLINA | Yes | In Progress | No | 2016-03-01 | 2016-04-04 |  |  |  | Orange County
2 | 4 | CHIQUITA |  | In Progress | No | 2016-03-02 | 2016-04-05 |  |  |  | Orange County
2 | 4 | CHIP |  | Abandoned | NA |  |  |  |  | CHIP shows up on ems as 66kv; Customer Sub | Orange County
2 | 4 | DIEMER |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | ELY |  | In Progress | No | 2016-03-02 | 2016-03-15 |  |  |  | Orange County
2 | 4 | ESTRELLA | Yes | In Progress | No | 2016-04-20 | 2016-04-27 |  |  | 1/12/2017 - Per Nancy, this contains duplicate ICCP objects from DVVC, so they have been deleted on the EMS side (see email) | Orange County
2 | 4 | FULLERTON | Yes | In Progress | No | 2016-04-20 | 2016-04-27 |  |  |  | Orange County
2 | 4 | GILBERT | Yes | In Progress | No | 2016-04-20 | 2016-04-29 |  |  |  | Orange County
2 | 4 | GISLER |  | In Progress | No | 2016-04-28 | 2016-05-02 |  |  |  | Orange County
2 | 4 | HAMILTON |  | In Progress | No | 2016-04-28 | 2016-05-04 |  |  |  | Orange County
2 | 4 | HUNTINGTON BEACH |  | Abandoned | NA |  |  |  |  | Generation Sub | Orange County
2 | 4 | KIWI |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | LA HABRA | Yes | In Progress | No | 2016-06-02 | 2016-06-09 |  |  |  | Orange County
2 | 4 | LA VETA |  | In Progress | No | 2016-06-02 | 2016-06-09 |  |  |  | Orange County
2 | 4 | LAFAYETTE |  | In Progress | No | 2016-06-02 | 2016-06-09 |  |  |  | Orange County
2 | 4 | LAMPSON |  | In Progress | No | 2016-06-17 | 2016-07-13 |  |  |  | Orange County
2 | 4 | LAS LOMAS | Yes | In Progress | No | 2016-06-17 | 2016-07-13 |  |  |  | Orange County
2 | 4 | LIMESTONE | Yes | In Progress | No | 2016-06-17 | 2016-07-13 |  |  |  | Orange County
2 | 4 | MARION |  | List Avail | No | [5 empty] | Orange County
2 | 4 | MODENA |  | List Avail | No | [5 empty] | Orange County
2 | 4 | NIGUEL |  | List Avail | No | [5 empty] | Orange County
2 | 4 | OCEANVIEW | Yes | List Avail | No | [5 empty] | Orange County
2 | 4 | OLINDA | Yes | List Avail | No | [5 empty] | Orange County
2 | 4 | ORANGE |  | List Avail | No | [5 empty] | Orange County
2 | 4 | ORCOSAN |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | PAPER |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | PARKWOOD |  | List Avail | No | [5 empty] | Orange County
2 | 4 | PLACENTIA |  | List Avail | No | [5 empty] | Orange County
2 | 4 | RECOVERY |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | SANTIAGO |  | List Avail | No | [5 empty] | Orange County
2 | 4 | SLATER |  |  | No | [5 empty] | Orange County
2 | 4 | SOCO |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | SULLIVAN |  |  | No | [5 empty] | Orange County
2 | 4 | TEAM |  |  | No | [5 empty] | Orange County
2 | 4 | TELEGRAPH |  |  | No | [5 empty] | Orange County
2 | 4 | TITANS |  | Abandoned | NA |  |  |  |  | Customer Sub | Orange County
2 | 4 | TRASK |  |  | No | [5 empty] | Orange County
2 | 4 | VERA |  |  | No | [5 empty] | Orange County
2 | 4 | VIEJO |  |  | No | [5 empty] | Orange County
2 | 4 | VILLA PARK |  |  | No | [5 empty] | Orange County
2 | 4 | WASHINGTON |  |  | No | [5 empty] | Orange County
2 | 4 | WAVE |  |  | No | [5 empty] | Orange County
2 | 4 | YORBA LINDA |  |  | No | [5 empty] | Orange County
3 | 5 | ARCH BEACH |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | BASTA |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | BAYSIDE | Yes |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | BRISTOL |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | BROADCOM P.T. |  | Abandoned | NA |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | BROOKHURST | Yes |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | CEDARWOOD |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | CHIQUITA | Yes |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | COSTA MESA |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | EDINGER |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | FRIENDLY HILLS |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | IRVINE PARK P.T. |  | Abandoned | NA |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | MADRONE P.T. |  | Abandoned | NA |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | O'NEILL | Yes |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | PAULARINO |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County
3 | 5 | PEBBLY BEACH |  |  | No |  |  |  |  | Added Station from Erfan's OC List | Orange County

## AbandonedList
StationName | Status | Notes | SwCtr
AMADOR | Abandoned
UNIVERSITY | Abandoned | Customer Sub | Orange County
APOLLO | Abandoned | Customer Sub | Orange County
BURPIT | Abandoned | Customer Sub | Orange County
CHIP | Abandoned | Customer Sub | Orange County
DIEMER | Abandoned | Customer Sub | Orange County
HUNTINGTON BEACH | Abandoned | Generation Sub | Orange County
KIWI | Abandoned | Customer Sub | Orange County
ORCOSAN | Abandoned | Customer Sub | Orange County
PAPER | Abandoned | Customer Sub | Orange County
RECOVERY | Abandoned | Customer Sub | Orange County
SOCO | Abandoned | Customer Sub | Orange County
TITANS | Abandoned | Customer Sub | Orange County
BROADCOM P.T. | Abandoned | Added Station from Erfan's OC List | Orange County
IRVINE PARK P.T. | Abandoned | Added Station from Erfan's OC List | Orange County
MADRONE P.T. | Abandoned | Added Station from Erfan's OC List | Orange County